## Project 1
To-do list
To be completed by: |  | All
Deadline: |  | 2018-04-15
Project 1
% done | Phase | Due By | Notes | Developer Comments
50% | Log In & Registration page |  | Patrick - Tweaks and small enhancements on course.
50% | Website Pages |  | Tetsuya - Main website pages development.
0% | Payment Page |  | Tetsuya - Develop fake page. Could include link to Payment facilitator
60% | Main Kanvass page |  | Stefan - Save, edit and create available. Finalising tool inclsion types such as twitter, graphs, etc.
80% | Widgets |  | Stefan - Widgets available for creation and formatted to accept all elements that are currently available for selection. Tweaks required on widget resizing and movement.
25% | Technical Spec Report |  | Mark - Over the break the tech spec template will be created. All need to keep track of any development tools or formats that will need to be noted on the spec. | Two possible templates saved on Slack for review by All.
0% | UX & Testing |  | All - Once the site is completed (or 95%) UX will need to be reviewed for any feature tweaks and testing will need to be completed in the last 2 weeks before submission,
50% | Database |  | Mlabs for dev / IBM for deployment - Tetsuya to review deployment
50% | Hosting |  | Mlabs for dev / IBM for deployment - Tetsuya to review deployment
0% | Security |  | ? - Possibly completed if we have time.
0% | Presentation |  | All - Will be given on the platform if possible.
20% | Website word content |  | Mark - Page structure needs to be confirmed. Once completed word inclusion for page elements will be discussed.